## Milestones
ARRL Club Grant Milestones
Club Name:
Template Revision: | Issue 1
Name of Author: | <Yout name and callsign>
Date Submitted: | <xx/yy/zz>
Instructions: | Please include milestones and owners for executing your project to completion. You should have milestones for each major step that you are planning to complete your project. Examples might include target dates for training plans, completing major equipment acquistion steps, assembly and testing of important equipment subsystems, etc. Note that you do not need to repate the dates for purchasing equipment that you covered in your budget but you should include a milestone for completing installation, setup, and testing of the equipment after you have it in place.
Date | Description | Why is this milestone important? | Who is responsible for completing the milestones | Milestone Dependencies | Notes and comments
<xx/yy/zz> | <Brief description of milestone> | <Example why the milestone is important? What does important part of your project is accomplished?> | <Responsible person or group> | <Indicate anything that needs to happen for this milestone to be accomplished> | <Additional information>

## Sample
ARRL Club Grant Milestones
Club Name: | Upper Utopia ARS
Template Revision: | Issue 1
Name of Author: | My Name, CALLSIGN
Date Submitted: | 2022-04-28
Instructions: | Please include milestones and owners for executing your project to completion. You should have milestones for each major step that you are planning to complete your project. Examples might include target dates for training plans, completing major equipment acquistion steps, assembly and testing of important equipment subsystems, etc. Note that you do not need to repate the dates for purchasing equipment that you covered in your budget but you should include a milestone for completing installation, setup, and testing of the equipment after you have it in place.
Date | Description | Why is this milestone important? | Who is responsible for completing the milestones | Milestone Dependencies | Notes and comments
2022-08-15 | Grant Funds Received from ARRL | Enables us to order equipment and begin conditioning our clubhouse for station installation | ARRL
o o o o o o
2022-09-06 | Power supplies, power distribution equipment, DC cables, etc. arrive | Need this equipment in hand to begin construction | Jack NE1YY | DXEngineering to ship components to arrive by 9/1/22 | All items appear to be in stock at DXE
2022-09-23 | Installation of power distribution system in club station complete. | Required to use equipment in club station and to complete station infrastructure before installation the rest of the requipment | Joe AB1XX | Need electrician to complete installation of new breaker panel and outlets.
o o o o o o